## Slide 1
Brampton Civic Hospital Relocation
Challenges,
Risks &
Realities

## Slide 2
HCR’s HISTORY – A BIT ABOUT US…
Since 1993 Health Care Relocations (HCR) has:
    Provided transition planning and physical relocation services exclusively to healthcare clients around the world
    Safely relocated more than 500 hospitals:
                Approximately 18.5 million m² of healthcare facilities
                Tens of thousands of patients safely transferred worldwide

## Slide 3
OUR OFFICE LOCATIONS

## Slide 4
THE HCR MANDATE…
Maintain Patient Focus
Minimize Downtime and Associated Costs
Mitigate Risk
For over 25 years, HCR has been planning & relocating hospitals.

## Slide 5
PRESENTATION OVERVIEW
This presentation will highlight critical lessons learned from one of Canada’s first major hospital relocation experiences in 2007
The lessons learned will review three essential relocation planning elements and how important it is to integrate the planning and execution processes through one central process, i.e. operational readiness, new hospital activation, physical relocation.
These relocation planning elements will also be examined on how they relate to our current work in Denmark.

## Slide 6
THE NEW BRAMPTON CIVIC HOSPITAL
Opened in 2007
One of Canada's first public hospitals to be designed, built, financed, and maintained under a private-public partnership (P3)
608 bed replacement facility
Serves approximately 500.000 residents in Brampton and the surrounding area
Built to accommodate 80.000 emergency patient visits and 201.000 ambulatory care visits annually
4.100 employees

## Slide 7
BRAMPTON CIVIC HOSPITAL LOCATION
Located in the Province of Ontario
Northwest of Toronto
  Close to the Toronto International Airport
  Part of the “Greater Toronto Area” catchment
Part of the William Osler Health System
  Brampton Civic Hospital
  Etobicoke General Hospital
  Peel Memorial

## Slide 8
CONSTRUCTION COST AND EQUIPMENT FUNDING
Total square meters: 120.800 m2
Total Construction Cost: $734 million (3,7 mia. DKK)
  original projection of $350 million (1,8 mia. DKK)
  significantly over budget predictions!
Additional New Equipment Costs: $56 million (282 mio. DKK) for diagnostic & medical equipment
$!

## Slide 9
WHAT WENT WELL
The Physical relocation to the new hospital was a great success
  Developed the relocation plan over a 2 year period including:
    the physical relocation of hospital furniture and equipment
    Patient Transfer planning
  Legacy hospital site was approximately 10 km away
  Developed a detailed 3-week relocation plan including:
    Relocation calendar and sequence
    Detailed department relocation plans
    Service level reduction plan / maintained urgent & emergent services

## Slide 10
WHAT WENT WELL
Patient Transfers
  The Patient Transfer Plan was supported by the relocation strategy & related service level reductions
  Successfully relocated 236 patients in approximately 5 hours

## Slide 11
WHAT WENT WRONG – OPERATIONAL START-UP
The public expected the new hospital to provide enhanced care with improved access to emergency care and decreased wait times
The hospital was not prepared to operate in the new building
  Staff and physicians struggled in an unfamiliar environment with too many changes
  20% more emergency-room traffic than predicted
  high acuity emergency patients doubled
  only 479 of the promised 608 beds were opened
The community was told that the new hospital would be:
“the Crown Jewel for Brampton & Ontario”
– Ontario Minister of Health prior to new hospital opening

## Slide 12
INSUFFICIENT OPERATIONAL READINESS PLANNING
Operational readiness was not well funded, planned, managed or monitored
  Insufficient development of new workflows
  Little or no integrated planning between critical departments
No formal project management structure or assigned project leads
  Executive leadership was responsible for the construction project & administering the hospital
  No dedicated move coordinators
  Poor communication of project planning information
  No risk management planning
  No change management planning

## Slide 13
INSUFFICIENT ORIENTATION & TRAINING
4,100 employees were provided with only 2 hours of building orientation & fire safety training
  Nurse Educators were to complete “on-the-job” training of new equipment at occupancy.
Importance of education and training was grossly underestimated
  It was thought that experienced staff and physicians would easily adapt to their new work environment.
“Physicians, nurses and staff didn't anticipate the challenges that would come with moving to a spanking new hospital, from mastering the computer system to finding the stairs.”
– News Media Report

## Slide 14
NO FACILITY ACTIVATION PLAN
Hospital handed over from construction with many uncorrected deficiencies
Short activation/operational commissioning period – 2 months to complete:
  Construction deficiencies and building commissioning activities
  Cleaning
  New furniture & equipment installations and commissioning
  IT hardware and telephone installations and testing
  Stocking of medical and non-medical supplies
  Clean linen applications, wall-hung installations
  No work flow simulations

## Slide 15
THE PERFECT STORM – WHAT MADE THE PROBLEMS WORSE
New building start-up challenges
    Operating room air exchange & laminar flow systems
    Insufficient emergency power to medically necessary equipment / generators not tested
    I.T. infrastructure issues
No post-move Activity Recovery Plan added to the operational risks
  No gradual return to post move activity & immediate start-up of expanded programs
  “business as usual” approach overwhelmed the hospital’s ability to respond to operational and building challenges
Hundreds of new & inexperienced staff hired to support expanded operations
  Insufficient training or support from existing staff that were struggling to adapt to the new hospital

## Slide 16
WHAT TRANSPIRED
Within weeks of opening, the new hospital became a public relations nightmare for staff and administrators
    allegations of mismanagement and substandard healthcare
    10 to 12 hours emergency wait times were reported
    2 patient deaths became the “lightning rod” for community outcry & distrust including 1 patient’s family who had donated $25,000 to the new hospital
    sparked street protests among the very community that helped raise funds for the project
Provincial Ministry of Health assigned a “supervisor” to review the problems and resolve the operational issues as quickly as possible
    3-months post move the Entire Executive Leadership Team resigned
    It took approximately 2-years to resolve the operational problems & return to post-move service levels

## Slide 17
LESSONS LEARNED
Planning for a new hospital is extensively more than just the design and construction phases
  Design is based on workflow concepts envisioned for the new hospital
  Conceptual design plans require detailed operational planning
Relocation planning includes three (3) important planning elements:
  Operational readiness
  New hospital activation
  Physical relocation including the patient transfers

## Slide 18
RELOCATION PLANNING ELEMENTS & INTEGRATION
First Patient Day
Normal
Activity
Construction Transition
From design to build, the bricks and mortar becomes a
FUNCTIONAL BUILDING
Hospital Transition
Beginning at substantial completion, the functional building becomes a FUNCTIONAL HOSPITAL
Physical Relocation Transition
During the relocation phase, the functional hospital becomes a
FULLY OPERATIONAL HOSPITAL
Relocation Planning
Operational Readiness
Orientation & Training
New Facility Activation
Physical Relocation
Patient Transfer
Execute Facility Activation Plan
New building readiness
Operational readiness validation/functionality testing
Simulations
Orientation & training
Mock Patient Move
Execute Relocation Plan
Execute Activity Reduction Plan
Execute Patient Transfer Plan
Execute Operational Readiness Plan
Execute Activity Recovery
Plan
Change and Risk Management
Move Phase
3
Facility Activation Phase
2
Construction Phase
1

## Slide 19
LESSONS LEARNED
Mitigate Project Management Risks
An effective project management organizational structure must be in place
Mitigate Building & Operational Readiness Risks
A detailed new hospital activation plan is required to support building and operational readiness from reception of the new building to First Patient Day
Requires a strategic approach to planning and a detailed Activation Schedule to support the execution process, i.e. 6 to 8-months

## Slide 20
LESSONS LEARNED
Mitigate Operational Risks
Operational readiness planning takes approximately 2 years
Critical to successful operational readiness:
  Develop new workflows for all departments
  Prioritize IT projects
  Workflow simulations must be completed to validate operational readiness
  Staff and physician orientation and training are essential
  Communication & change management
Wherever possible, new workflows, small medical equipment and IT changes should be implemented at the legacy hospital

## Slide 21
LESSONS LEARNED – SUMMARY
Change during transition to a new hospital is not an event; it is a process that should not be under-estimated!
Relocation planning = government and hospital corporate priority
Ownership and accountability = Sustainability
Be flexible, adaptable, supportive and be kind to each other…it’s an exciting but challenging period in the hospital’s history

## Slide 22
?
QUESTIONS